## Outage
Event ID | Unit ID | Event Type | Status | Estimated Start Date | Estimated End Date | Actual Start Date | Actual End Date | ISO ID | Iso Status | Iso Type | Max Capability | Curtailment | Avail Cap | Reason | Modifier | Modified Date
7971787 | AGAVE BESS | PE | in_progress | 04/13/2026 10:00:00 | 05/31/2026 18:00:00 | 04/13/2026 10:00:00 |  |  |  | MW | 150 | 150 | 0 | APS IT/APS RenGen/Vertech work on RTAC | Z17513 | 05/07/2026 12:20:01 MST
6618226 | ARLINGTON CC CT A | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:03:52 MST
8936531 | ARLINGTON CC CT A | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:05:16 MST
11107880 | ARLINGTON CC CT A | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:06:24 MST
12892971 | ARLINGTON CC CT A | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:07:15 MST
7457239 | ARLINGTON CC CT B | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:04:07 MST
5310223 | ARLINGTON CC CT B | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:05:28 MST
15533785 | ARLINGTON CC CT B | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:06:35 MST
16345091 | ARLINGTON CC CT B | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 124 | 124 | 0 | Unit out of season | Z13288 | 10/23/2024 13:07:23 MST
5953299 | ARLINGTON CC DB+CH | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 565 | 565 | 0 | Unit out of season | Z13288 | 10/23/2024 13:03:42 MST
14422005 | ARLINGTON CC DB+CH | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 565 | 565 | 0 | Unit out of season | Z13288 | 10/23/2024 13:05:07 MST
7772647 | ARLINGTON CC DB+CH | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 565 | 565 | 0 | Unit out of season | Z13288 | 10/23/2024 13:06:12 MST
9209447 | ARLINGTON CC DB+CH | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 565 | 565 | 0 | Unit out of season | Z13288 | 10/23/2024 13:07:07 MST
10222473 | ARLINGTON CC ST | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 235 | 235 | 0 | Unit out of season | Z13288 | 10/23/2024 13:03:21 MST
12106469 | ARLINGTON CC ST | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 235 | 235 | 0 | Unit out of season | Z13288 | 10/23/2024 13:04:29 MST
3327563 | ARLINGTON CC ST | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 235 | 235 | 0 | Unit out of season | Z13288 | 10/23/2024 13:06:01 MST
1889639 | ARLINGTON CC ST | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 235 | 235 | 0 | Unit out of season | Z13288 | 10/23/2024 13:06:56 MST
10931151 | CATCLAW BESS PPA | PO | in_progress | 05/21/2026 07:30:00 | 05/21/2026 15:00:00 | 05/21/2026 07:30:00 | 05/21/2026 15:00:00 |  |  | MW | 250 | 250 | 0 | APS is requesting a generation only outage for Catclaw SLR and BESS for meter reprogramming. During this time we will lose all indication of the site so we need the PV and BESS at zero for the duration of the outage. Start : 5/21/26 0730 End: 5/21/26 1500 | Z17267 | 05/21/2026 15:00:40 MST
628128 | CATCLAW BESS PPA | U1 | canceled | 05/27/2026 11:15:00 | 05/28/2026 11:00:00 |  |  |  |  | MW | 250 | 250 | 0 | UAT Testing - Alain | Z11064 | 04/28/2026 11:51:54 MST
31529 | CATCLAW BESS PPA | U1 | canceled | 05/29/2026 11:52:00 | 05/30/2026 11:00:00 |  |  |  |  | MW | 250 | 250 | 0 | UAT Testing - Alain | Z11064 | 04/28/2026 12:22:05 MST
9139570 | CATCLAW SOLAR PPA | PO | in_progress | 05/21/2026 07:30:00 | 05/21/2026 15:00:00 | 05/21/2026 07:30:00 | 05/21/2026 15:00:00 |  |  | MW | 225 | 225 | 0 | APS is requesting a generation only outage for Catclaw SLR and BESS for meter reprogramming. During this time we will lose all indication of the site so we need the PV and BESS at zero for the duration of the outage. Start : 5/21/26 0730 End: 5/21/26 1500 | Z19944 | 05/21/2026 15:00:26 MST
12814028 | CE TURBO | U1 | in_progress | 07/18/2025 15:00:00 | 10/25/2026 23:59:00 | 07/18/2025 14:28:00 |  |  |  | MW | 12 | 12 | 0 | In outage - attempt to return 07/19 morning Contracts update 8/14/25 - CE Turbo is unavailable until further notice Contracts update 8/29/25 - • End of Q4 2025: A return-to-service plan will be provided to APS, or the unit may be declared irreparable by CE Turbo. | Z13288 | 05/11/2026 11:01:35 MST
10408574 | CHINO VALLEY | PO | in_progress | 03/22/2027 07:00:00 | 03/24/2027 14:00:00 |  |  |  | Approved | MW | 20 | 20 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
13347858 | CHINO VALLEY | PO | in_progress | 03/26/2029 07:00:00 | 03/28/2029 14:00:00 |  |  |  | Approved | MW | 20 | 20 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
6072443 | CHINO VALLEY | PO | in_progress | 03/24/2031 07:00:00 | 03/26/2031 14:00:00 |  |  |  | Approved | MW | 20 | 20 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
8159270 | CHOLLA 1 | U1 | in_progress | 02/25/2025 16:34:00 | 12/31/2026 23:59:00 | 02/25/2025 10:21:00 |  |  |  | MW | 112 | 112 | 0 | CH U1 Tripped offline at 1021 due to loss of Coal | Z18263 | 03/30/2026 08:49:57 MST
4032713 | CHOLLA 3 | U1 | in_progress | 03/17/2025 15:48:00 | 12/31/2026 23:59:00 | 03/17/2025 14:54:00 |  |  |  | MW | 268 | 268 | 0 | U3 offline at 1454 hours. | Z18263 | 03/30/2026 08:50:37 MST
12140493 | COTTON CENTER | PO | in_progress | 03/15/2028 07:00:00 | 03/17/2028 14:00:00 |  |  |  | Approved | MW | 17 | 17 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
14757710 | COTTON CENTER | PO | in_progress | 03/13/2030 07:00:00 | 03/15/2030 14:00:00 |  |  |  | Approved | MW | 17 | 17 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
14924778 | DESERT BLOOM BESS PPA | U1 | canceled | 06/02/2026 09:19:00 | 06/03/2026 09:00:00 |  |  |  |  | MW | 150 | 150 | 0 | UAT Testing - Alain | Z11064 | 05/05/2026 09:27:10 MST
8898606 | DESERT STAR | PO | in_progress | 03/24/2027 07:00:00 | 03/26/2027 14:00:00 |  |  |  | Approved | MW | 10 | 10 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
14011451 | DESERT STAR | PO | in_progress | 03/28/2029 07:00:00 | 03/30/2029 14:00:00 |  |  |  | Approved | MW | 10 | 10 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
5620892 | DESERT STAR | PO | in_progress | 03/26/2031 07:00:00 | 03/28/2031 14:00:00 |  |  |  | Approved | MW | 10 | 10 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
4272228 | DESERT STAR BESS | U1 | in_progress | 05/19/2026 19:05:00 | 05/22/2026 16:00:00 | 05/19/2026 18:08:00 |  |  |  | MW | 10 | 10 | 0 | Desert Star BESS: Unavailable due to Mvar oscillation As of: 05/19/2026, at 1808 hrs ERTFL 05/21/2026 at 1600 hrs RTS extended to 05/22/2026, at 1600hrs. | Z17267 | 05/21/2026 14:03:01 MST
4471393 | DOUGLAS GT1 | PO | pending | 10/01/2026 06:00:00 | 11/14/2026 18:00:00 |  |  |  |  | MW | 15 | 15 | 0 | Relay Replacement outage | Z05860 | 05/08/2026 05:41:14 MST
7523651 | DOUGLAS GT1 | PO | in_progress | 04/12/2027 06:00:00 | 04/22/2027 20:00:00 |  |  |  | Approved | MW | 16 | 16 | 0 | Planned reliability outage SA255930 | Z05860 | 06/26/2025 06:15:30 MST
11041569 | DOUGLAS GT1 | PO | in_progress | 04/10/2028 06:00:00 | 04/20/2028 20:00:00 |  |  |  | Approved | MW | 16 | 16 | 0 | Planned reliability outage. | integ-mig | 12/31/2023 22:00:00 MST
9562004 | DOUGLAS GT1 | PO | in_progress | 04/16/2029 06:00:00 | 04/26/2029 20:00:00 |  |  |  | Approved | MW | 16 | 16 | 0 | Planned reliability outage. | integ-mig | 12/31/2023 22:00:00 MST
1216651 | DOUGLAS GT1 | PO | in_progress | 04/15/2030 06:00:00 | 04/25/2030 20:00:00 |  |  |  | Approved | MW | 16 | 16 | 0 | Planned reliability outage. | integ-mig | 12/31/2023 22:00:00 MST
1695745 | DOUGLAS GT1 | PO | in_progress | 04/14/2031 06:00:00 | 04/24/2031 20:00:00 |  |  |  | Approved | MW | 16 | 16 | 0 | Planned reliability outage. | integ-mig | 12/31/2023 22:00:00 MST
10722637 | FOOTHILLS | PO | in_progress | 03/08/2027 07:00:00 | 03/15/2027 14:00:00 |  |  |  | Approved | MW | 38 | 38 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
11083964 | FOOTHILLS | PO | in_progress | 03/05/2029 07:00:00 | 03/12/2029 14:00:00 |  |  |  | Approved | MW | 38 | 38 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
7542018 | FOOTHILLS | PO | in_progress | 03/03/2031 07:00:00 | 03/10/2031 14:00:00 |  |  |  | Approved | MW | 38 | 38 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
10242551 | FOUR CORNERS 4 | PO | in_progress | 03/13/2027 00:00:00 | 03/27/2027 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (15 days) - SCR Catalyst Replacement | integ-mig | 12/31/2023 22:00:00 MST
10899339 | FOUR CORNERS 4 | PO | in_progress | 02/18/2028 00:00:00 | 03/18/2028 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Minor Outage (32 days) | Z13288 | 04/07/2026 12:45:04 MST
3269857 | FOUR CORNERS 4 | PO | in_progress | 03/03/2029 00:00:00 | 03/14/2029 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (12 days) | Z13288 | 07/02/2025 09:08:18 MST
5737299 | FOUR CORNERS 4 | PO | in_progress | 03/09/2030 00:00:00 | 03/26/2030 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (18 days) - SCR Catalyst Replacement | Z13288 | 04/07/2026 12:46:11 MST
9413250 | FOUR CORNERS 5 | PO | in_progress | 04/17/2027 00:00:00 | 05/03/2027 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (18 days) | Z13288 | 04/07/2026 12:46:49 MST
184647 | FOUR CORNERS 5 | PO | in_progress | 04/08/2028 00:00:00 | 05/09/2028 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Minor Outage (32 days) | Z13288 | 04/07/2026 12:50:11 MST
3971412 | FOUR CORNERS 5 | PO | in_progress | 04/07/2029 00:00:00 | 04/24/2029 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (18 days) - SCR Catalyst Replacement | Z13288 | 04/07/2026 12:50:30 MST
14318788 | FOUR CORNERS 5 | PO | in_progress | 04/13/2030 00:00:00 | 04/24/2030 23:59:00 |  |  |  | Approved | MW | 770 | 770 | 0 | Reliability Outage (12 days) | integ-mig | 12/31/2023 22:00:00 MST
16560032 | GILA BEND | PO | in_progress | 03/13/2028 07:00:00 | 03/16/2028 14:00:00 |  |  |  | Approved | MW | 18 | 18 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
10585523 | GILA BEND | PO | in_progress | 03/11/2030 07:00:00 | 03/14/2030 14:00:00 |  |  |  | Approved | MW | 18 | 18 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
4678335 | GRIFFITH CC DB+CH | PO | in_progress | 10/01/2025 00:00:00 | 05/31/2026 23:59:00 | 10/01/2025 00:00:00 |  |  |  | MW | 570 | 570 | 0 | Unit out of season | Z13288 | 12/29/2025 11:06:33 MST
15551184 | GRIFFITH CC DB+CH | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 570 | 570 | 0 | Unit out of season | Z13288 | 10/23/2024 13:22:07 MST
14966939 | GRIFFITH CC DB+CH | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 570 | 570 | 0 | Unit out of season | Z13288 | 10/23/2024 13:22:55 MST
2159533 | GRIFFITH CC DB+CH | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 570 | 570 | 0 | Unit out of season | Z13288 | 10/23/2024 13:23:47 MST
8950081 | GRIFFITH CC DB+CH | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 570 | 570 | 0 | Unit out of season | Z13288 | 10/23/2024 13:24:43 MST
5926706 | GRIFFITH CTA | PO | in_progress | 10/01/2025 00:00:00 | 05/31/2026 23:59:00 | 10/01/2025 00:00:00 |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 12/29/2025 11:06:44 MST
10663715 | GRIFFITH CTA | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:22:18 MST
7402140 | GRIFFITH CTA | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:23:04 MST
13927592 | GRIFFITH CTA | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:23:56 MST
13841515 | GRIFFITH CTA | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:24:52 MST
3543264 | GRIFFITH CTB | PO | in_progress | 10/01/2025 00:00:00 | 05/31/2026 23:59:00 | 10/01/2025 00:00:00 |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 12/29/2025 11:06:54 MST
11332331 | GRIFFITH CTB | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:22:29 MST
10363771 | GRIFFITH CTB | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:23:14 MST
8603484 | GRIFFITH CTB | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:24:08 MST
13202294 | GRIFFITH CTB | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:25:02 MST
8375911 | GRIFFITH ST | PO | in_progress | 10/01/2025 00:00:00 | 05/31/2026 23:59:00 | 10/01/2025 00:00:00 |  |  |  | MW | 275 | 275 | 0 | Unit out of season | Z13288 | 12/29/2025 11:06:14 MST
9281984 | GRIFFITH ST | PO | in_progress | 09/30/2026 23:59:00 | 05/31/2027 23:59:00 |  |  |  |  | MW | 275 | 275 | 0 | Unit out of season | Z13288 | 10/23/2024 13:21:57 MST
12540737 | GRIFFITH ST | PO | in_progress | 09/30/2027 23:59:00 | 05/31/2028 23:59:00 |  |  |  |  | MW | 275 | 275 | 0 | Unit out of season | Z13288 | 10/23/2024 13:22:46 MST
13483806 | GRIFFITH ST | PO | in_progress | 09/30/2028 23:59:00 | 05/31/2029 23:59:00 |  |  |  |  | MW | 275 | 275 | 0 | Unit out of season | Z13288 | 10/23/2024 13:23:33 MST
3822094 | GRIFFITH ST | PO | in_progress | 09/30/2029 23:59:00 | 05/31/2030 23:59:00 |  |  |  |  | MW | 275 | 275 | 0 | Unit out of season | Z13288 | 10/23/2024 13:24:27 MST
1852805 | HARQUAHALA SUN | PO | canceled | 05/26/2026 07:30:00 | 05/26/2026 15:00:00 |  |  |  |  | MW | 300 | 300 | 0 | Per Harquahala ROC, the original full-site outage for 5/14 got moved to 5/26. | Z19944 | 05/14/2026 09:13:35 MST
8237358 | HARQUAHALA SUN | MO | canceled | 05/26/2026 07:30:00 | 05/26/2026 15:00:00 |  |  |  |  | MW | 300 | 300 | 0 | Per Harquahala ROC, the original outage for 5/14 both halves of the site got moved to 5/26. | Z18263 | 05/15/2026 13:20:09 MST
14477295 | HARQUAHALA SUN BESS | MO | canceled | 05/26/2026 07:30:00 | 05/26/2026 15:00:00 |  |  |  |  | MW | 300 | 300 | 0 | HARQ2 BESS - APS Meter Work | Z18263 | 05/15/2026 13:21:07 MST
5840563 | HYDER I | MO | in_progress | 06/01/2026 08:00:00 | 06/12/2026 17:00:00 |  |  |  |  | MW | 15 | 15 | 0 | outage for Invenergy cutover | Z18263 | 04/28/2026 12:44:08 MST
1035259 | HYDER I | PO | in_progress | 03/27/2028 07:00:00 | 03/29/2028 14:00:00 |  |  |  | Approved | MW | 15 | 15 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
14470131 | HYDER I | PO | in_progress | 03/25/2030 07:00:00 | 03/27/2030 14:00:00 |  |  |  | Approved | MW | 15 | 15 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
6184332 | HYDER I BESS | MO | in_progress | 06/01/2026 08:00:00 | 06/12/2026 17:00:00 |  |  |  |  | MW | 16 | 16 | 0 | outage for Invenergy cutover | Z18263 | 04/28/2026 12:44:12 MST
7928376 | HYDER II | MO | in_progress | 06/01/2026 08:00:00 | 06/12/2026 17:00:00 |  |  |  |  | MW | 14 | 14 | 0 | outage for Invenergy cutover | Z18263 | 04/28/2026 12:44:16 MST
3991184 | HYDER II | PO | in_progress | 03/29/2028 07:00:00 | 03/31/2028 14:00:00 |  |  |  | Approved | MW | 14 | 14 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
10788576 | HYDER II | PO | in_progress | 03/27/2030 07:00:00 | 03/29/2030 14:00:00 |  |  |  | Approved | MW | 14 | 14 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
3005280 | HYDER II BESS | MO | in_progress | 06/01/2026 08:00:00 | 06/12/2026 17:00:00 |  |  |  |  | MW | 14 | 14 | 0 | outage for Invenergy cutover | Z18263 | 04/28/2026 12:44:19 MST
9496225 | KITT PPA | U1 | canceled | 05/29/2026 11:54:00 | 05/30/2026 11:00:00 |  |  |  |  | MW | 100 | 100 | 0 | UAT Testing - Alain | Z11064 | 04/28/2026 12:22:10 MST
10276687 | LUKE | MO | canceled | 06/09/2026 07:00:00 | 06/11/2029 19:00:00 |  |  |  |  | MW | 11 | 11 | 0 | outage for transmission work that will cause loss of visibility | Z19944 | 05/12/2026 13:42:51 MST
9195869 | LUKE | PO | in_progress | 03/06/2028 07:00:00 | 03/08/2028 14:00:00 |  |  |  | Approved | MW | 11 | 11 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
10649310 | LUKE | PO | in_progress | 03/04/2030 07:00:00 | 03/06/2030 14:00:00 |  |  |  | Approved | MW | 11 | 11 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
325896 | MARICOPA ENERGY CENTER 1 BESS | U1 | canceled | 05/27/2026 11:31:00 | 05/28/2026 11:00:00 |  |  |  |  | MW | 183 | 183 | 0 | UAT Testing - Alain | Z11064 | 04/28/2026 11:49:39 MST
1891152 | MARICOPA ENERGY CENTER 1 BESS | U1 | canceled | 05/29/2026 11:52:00 | 05/30/2026 11:00:00 |  |  |  |  | MW | 183 | 183 | 0 | UAT Testing - Alain | Z11064 | 04/28/2026 12:22:00 MST
10286775 | MARICOPA ENERGY CENTER 1 BESS | PO | in_progress | 10/27/2026 20:00:00 | 10/28/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 BESS Substation preventive maintenance | Z18263 | 04/28/2026 07:14:19 MST
7563332 | MARICOPA ENERGY CENTER 1 BESS | PO | in_progress | 10/28/2026 20:00:00 | 10/29/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 BESS Substation preventive maintenance | Z18263 | 04/28/2026 07:16:08 MST
9707433 | MARICOPA ENERGY CENTER 1 BESS | PO | in_progress | 10/29/2026 20:00:00 | 10/30/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 BESS Substation preventive maintenance | Z18263 | 04/28/2026 07:15:59 MST
3743764 | MARICOPA ENERGY CENTER 1 SOLAR PPA | PO | in_progress | 10/27/2026 20:00:00 | 10/28/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 PV Substation preventive maintenance | Z18263 | 04/28/2026 07:17:31 MST
10569907 | MARICOPA ENERGY CENTER 1 SOLAR PPA | PO | in_progress | 10/28/2026 20:00:00 | 10/29/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 PV Substation preventive maintenance | Z18263 | 04/28/2026 07:19:14 MST
4634706 | MARICOPA ENERGY CENTER 1 SOLAR PPA | PO | in_progress | 10/29/2026 20:00:00 | 10/30/2026 05:00:00 |  |  |  |  | MW | 183 | 183 | 0 | MEC Phase 1 PV Substation preventive maintenance | Z18263 | 04/28/2026 07:19:48 MST
10643212 | MARICOPA ENERGY CENTER 2 BESS | PO | in_progress | 10/28/2026 20:00:00 | 10/29/2026 05:00:00 |  |  |  |  | MW | 367 | 367 | 0 | MEC Phase 2 BESS & PV Substation preventive maintenance | Z18263 | 04/28/2026 07:21:53 MST
15119334 | MARICOPA ENERGY CENTER 2 BESS | PO | in_progress | 10/29/2026 20:00:00 | 10/30/2026 05:00:00 |  |  |  |  | MW | 367 | 367 | 0 | MEC Phase 2 BESS & PV Substation preventive maintenance | Z18263 | 04/28/2026 07:22:21 MST
11399953 | OCOTILLO CT3 | MO | in_progress | 05/28/2026 08:00:00 | 05/28/2026 12:00:00 |  |  |  |  | MW | 106 | 106 | 0 | Accelerometer replacement for summer reliability. | Z18263 | 05/21/2026 07:50:54 MST
11781473 | OCOTILLO CT3 | PO | in_progress | 10/04/2026 22:00:00 | 10/20/2026 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage OC292531 3-5 Blade replacement needing 14 day outage. CO Catalyst and AIG replacement OCC017749 | Z13288 | 04/16/2026 11:07:23 MST
13059110 | OCOTILLO CT3 | PO | in_progress | 01/20/2027 22:00:00 | 01/29/2027 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage OC292095 | Z05860 | 06/26/2025 06:14:58 MST
932185 | OCOTILLO CT3 | PO | in_progress | 10/03/2027 22:00:00 | 10/08/2027 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16571493 | OCOTILLO CT3 | PO | in_progress | 01/09/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
1655197 | OCOTILLO CT3 | PO | in_progress | 01/19/2028 22:00:00 | 01/28/2028 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
292628 | OCOTILLO CT3 | PO | in_progress | 10/08/2028 22:00:00 | 10/13/2028 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
5969914 | OCOTILLO CT3 | PO | in_progress | 01/17/2029 22:00:00 | 01/26/2029 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
14383157 | OCOTILLO CT3 | PO | in_progress | 10/07/2029 22:00:00 | 10/12/2029 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7133871 | OCOTILLO CT3 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 107 | 107 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:11 MST
3579585 | OCOTILLO CT3 | PO | in_progress | 01/13/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
3826966 | OCOTILLO CT3 | PO | in_progress | 01/23/2030 22:00:00 | 02/01/2030 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
5347594 | OCOTILLO CT3 | PO | in_progress | 10/06/2030 22:00:00 | 10/11/2030 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
13582863 | OCOTILLO CT3 | PO | in_progress | 01/22/2031 22:00:00 | 01/31/2031 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
12430455 | OCOTILLO CT3 | PO | in_progress | 10/05/2031 22:00:00 | 10/10/2031 18:00:00 |  |  |  | Approved | MW | 107 | 107 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7357393 | OCOTILLO CT4 | PO | in_progress | 10/11/2026 22:00:00 | 10/16/2026 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage OC292622 | Z05860 | 06/26/2025 06:00:23 MST
11173046 | OCOTILLO CT4 | PO | in_progress | 01/31/2027 22:00:00 | 02/09/2027 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage OC292161 | Z05860 | 06/26/2025 06:14:38 MST
11038998 | OCOTILLO CT4 | PO | in_progress | 10/10/2027 22:00:00 | 10/15/2027 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
15573413 | OCOTILLO CT4 | PO | in_progress | 01/09/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
13065831 | OCOTILLO CT4 | PO | in_progress | 01/30/2028 22:00:00 | 02/08/2028 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
6952713 | OCOTILLO CT4 | PO | in_progress | 10/15/2028 22:00:00 | 10/20/2028 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
13752461 | OCOTILLO CT4 | PO | in_progress | 01/28/2029 22:00:00 | 02/06/2029 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1683456 | OCOTILLO CT4 | PO | in_progress | 10/14/2029 22:00:00 | 10/19/2029 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16430626 | OCOTILLO CT4 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 103 | 103 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:44 MST
9653272 | OCOTILLO CT4 | PO | in_progress | 01/13/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
1834676 | OCOTILLO CT4 | PO | in_progress | 02/03/2030 22:00:00 | 02/12/2030 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
6607087 | OCOTILLO CT4 | PO | in_progress | 10/13/2030 22:00:00 | 10/18/2030 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
6580481 | OCOTILLO CT4 | PO | in_progress | 02/02/2031 22:00:00 | 02/11/2031 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
2246710 | OCOTILLO CT4 | PO | in_progress | 10/12/2031 22:00:00 | 10/17/2031 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
5430511 | OCOTILLO CT5 | MO | in_progress | 05/21/2026 08:00:00 | 05/21/2026 15:00:00 | 05/21/2026 08:00:00 | 05/21/2026 15:00:00 |  |  | MW | 105 | 105 | 0 | OC5 outage for IPT borescope and water wash. | Z19944 | 05/21/2026 15:46:04 MST
1030545 | OCOTILLO CT5 | U1 | in_progress | 05/21/2026 15:45:00 | 05/26/2026 18:00:00 | 05/21/2026 15:00:00 |  |  |  | MW | 105 | 105 | 0 | Ocotillo GT5 Borescope inspection revealed IPT and PT damage. GE dispatching technician to perform their own Borescope, update to be provided by 1800 Tuesday 5/26. | Z19944 | 05/21/2026 15:45:53 MST
11284996 | OCOTILLO CT5 | PO | in_progress | 10/18/2026 22:00:00 | 10/23/2026 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage OC292777 | Z05860 | 06/26/2025 06:00:51 MST
10719624 | OCOTILLO CT5 | PO | in_progress | 02/11/2027 22:00:00 | 02/20/2027 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage OC292291 | Z05860 | 06/26/2025 06:14:13 MST
14763389 | OCOTILLO CT5 | PO | in_progress | 10/17/2027 22:00:00 | 10/22/2027 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16516363 | OCOTILLO CT5 | PO | in_progress | 01/09/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
5170568 | OCOTILLO CT5 | PO | in_progress | 02/10/2028 22:00:00 | 02/19/2028 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
9373254 | OCOTILLO CT5 | PO | in_progress | 10/22/2028 22:00:00 | 10/27/2028 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16303596 | OCOTILLO CT5 | PO | in_progress | 02/08/2029 22:00:00 | 02/17/2029 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
10708036 | OCOTILLO CT5 | PO | in_progress | 10/21/2029 22:00:00 | 10/26/2029 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7353506 | OCOTILLO CT5 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 105 | 105 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:50 MST
10813793 | OCOTILLO CT5 | PO | in_progress | 01/13/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
7642571 | OCOTILLO CT5 | PO | in_progress | 02/14/2030 22:00:00 | 02/23/2030 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16562989 | OCOTILLO CT5 | PO | in_progress | 10/20/2030 22:00:00 | 10/25/2030 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
13799203 | OCOTILLO CT5 | PO | in_progress | 02/13/2031 22:00:00 | 02/22/2031 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
8146185 | OCOTILLO CT5 | PO | in_progress | 10/19/2031 22:00:00 | 10/24/2031 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
10778363 | OCOTILLO CT6 | PE | in_progress | 05/04/2026 18:01:00 | 05/22/2026 23:59:00 | 05/04/2026 18:01:00 |  |  |  | MW | 101 | 101 | 0 | Tripped during last scheduled MR due to vibrational issues. GE engineering reviewing data and providing next steps Next update 5/6 1800. | Z17429 | 05/19/2026 07:59:04 MST
6782114 | OCOTILLO CT6 | PO | in_progress | 10/25/2026 22:00:00 | 10/30/2026 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage OC292811 | Z05860 | 06/26/2025 06:01:18 MST
6792523 | OCOTILLO CT6 | PO | in_progress | 02/22/2027 22:00:00 | 03/03/2027 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage OC292227 | Z05860 | 06/26/2025 06:13:54 MST
10033375 | OCOTILLO CT6 | PO | in_progress | 10/24/2027 22:00:00 | 10/29/2027 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1789739 | OCOTILLO CT6 | PO | in_progress | 01/09/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
11003504 | OCOTILLO CT6 | PO | in_progress | 02/21/2028 22:00:00 | 03/01/2028 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
4086347 | OCOTILLO CT6 | PO | in_progress | 10/29/2028 22:00:00 | 11/03/2028 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
4520927 | OCOTILLO CT6 | PO | in_progress | 02/19/2029 22:00:00 | 02/28/2029 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
11799902 | OCOTILLO CT6 | PO | in_progress | 10/28/2029 22:00:00 | 11/02/2029 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
3262252 | OCOTILLO CT6 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 103 | 103 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:53 MST
9430711 | OCOTILLO CT6 | PO | in_progress | 01/13/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
3069864 | OCOTILLO CT6 | PO | in_progress | 02/25/2030 22:00:00 | 03/06/2030 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1799132 | OCOTILLO CT6 | PO | in_progress | 10/27/2030 22:00:00 | 11/01/2030 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7587181 | OCOTILLO CT6 | PO | in_progress | 02/24/2031 22:00:00 | 03/05/2031 18:00:00 |  |  |  | Approved | MW | 103 | 103 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
5915888 | OCOTILLO CT6 | PO | in_progress | 10/26/2031 22:00:00 | 10/31/2031 18:00:00 |  |  |  | Approved | MW | 101 | 101 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
588065 | OCOTILLO CT7 | MO | in_progress | 05/29/2026 08:00:00 | 05/29/2026 14:00:00 |  |  |  |  | MW | 105 | 105 | 0 | OC7 MO for post top case borescope inspection. | Z18263 | 05/21/2026 08:41:42 MST
14460968 | OCOTILLO CT7 | PO | in_progress | 11/23/2026 22:00:00 | 12/16/2026 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage OC292843 | Z13288 | 04/16/2026 11:07:00 MST
576568 | OCOTILLO CT7 | PO | in_progress | 03/05/2027 22:00:00 | 03/14/2027 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage OC292973 | Z05860 | 06/26/2025 06:13:31 MST
274236 | OCOTILLO CT7 | PO | in_progress | 10/31/2027 22:00:00 | 11/05/2027 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
2263982 | OCOTILLO CT7 | PO | in_progress | 01/09/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
14549478 | OCOTILLO CT7 | PO | in_progress | 03/03/2028 22:00:00 | 03/12/2028 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
847855 | OCOTILLO CT7 | PO | in_progress | 11/05/2028 22:00:00 | 11/10/2028 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
15826065 | OCOTILLO CT7 | PO | in_progress | 03/02/2029 22:00:00 | 03/11/2029 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7926835 | OCOTILLO CT7 | PO | in_progress | 11/04/2029 22:00:00 | 11/09/2029 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7640374 | OCOTILLO CT7 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 105 | 105 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:56 MST
2047259 | OCOTILLO CT7 | PO | in_progress | 01/13/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
6895569 | OCOTILLO CT7 | PO | in_progress | 03/08/2030 22:00:00 | 03/17/2030 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
12527617 | OCOTILLO CT7 | PO | in_progress | 11/03/2030 22:00:00 | 11/08/2030 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
348405 | OCOTILLO CT7 | PO | in_progress | 03/07/2031 22:00:00 | 03/16/2031 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
5937762 | OCOTILLO CT7 | PO | in_progress | 11/02/2031 22:00:00 | 11/07/2031 18:00:00 |  |  |  | Approved | MW | 105 | 105 | 0 | Planned Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1612337 | OCOTILLO GT1 | MO | in_progress | 05/22/2026 07:00:00 | 05/22/2026 18:00:00 | 05/22/2026 07:00:00 |  |  |  | MW | 50 | 50 | 0 | MO for CO2 cardox AC compressor maintenance. | Z17513 | 05/22/2026 07:01:19 MST
12191590 | OCOTILLO GT1 | PO | pending | 11/17/2026 00:01:00 | 12/18/2026 18:00:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Unit Outage (Ten Year Schedule) | Z13288 | 02/13/2026 12:42:31 MST
12385442 | OCOTILLO GT1 | PO | pending | 11/09/2027 00:01:00 | 11/19/2027 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage OC293039 | Z05860 | 06/26/2025 06:16:24 MST
685089 | OCOTILLO GT1 | PO | in_progress | 01/06/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 56 | 56 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
13537606 | OCOTILLO GT1 | PO | pending | 11/07/2028 00:01:00 | 11/17/2028 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/22/2024 10:37:47 MST
3509359 | OCOTILLO GT1 | PO | pending | 11/06/2029 00:01:00 | 11/16/2029 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/22/2024 10:37:56 MST
10805248 | OCOTILLO GT1 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 56 | 56 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:48:59 MST
13578321 | OCOTILLO GT1 | PO | in_progress | 01/10/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 56 | 56 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
16588141 | OCOTILLO GT1 | PO | pending | 11/05/2030 00:01:00 | 11/15/2030 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/22/2024 10:51:22 MST
14909745 | OCOTILLO GT1 | PO | pending | 11/04/2031 00:01:00 | 11/14/2031 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/22/2024 10:51:20 MST
7851293 | OCOTILLO GT2 | MO | in_progress | 05/22/2026 07:00:00 | 05/22/2026 18:00:00 | 05/22/2026 07:00:00 |  |  |  | MW | 50 | 50 | 0 | MO for CO2 cardox AC compressor maintenance. | Z17513 | 05/22/2026 07:01:15 MST
2457833 | OCOTILLO GT2 | PO | pending | 10/12/2026 00:01:00 | 11/10/2026 18:00:00 |  |  |  |  | MW | 50 | 50 | 0 | Planned Unit Outage (Ten Year Schedule) | Z13288 | 02/13/2026 12:43:01 MST
630564 | OCOTILLO GT2 | PO | pending | 11/23/2027 00:01:00 | 12/03/2027 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage OC 292424 | Z05860 | 06/26/2025 06:16:54 MST
16452278 | OCOTILLO GT2 | PO | in_progress | 01/06/2028 22:00:00 | 01/13/2028 16:00:00 |  |  |  | Approved | MW | 56 | 56 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
1682380 | OCOTILLO GT2 | PO | pending | 11/28/2028 00:01:00 | 12/08/2028 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/23/2024 10:49:46 MST
10341444 | OCOTILLO GT2 | PO | pending | 11/06/2029 00:01:00 | 11/16/2029 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/23/2024 11:00:59 MST
11109761 | OCOTILLO GT2 | PO | pending | 11/25/2029 23:59:00 | 12/08/2029 18:00:00 |  |  |  |  | MW | 56 | 56 | 0 | Fall BOP Outage & Circulating Watter Pipe inspection | Z03344 | 10/21/2024 21:49:04 MST
10250928 | OCOTILLO GT2 | PO | in_progress | 01/10/2030 22:00:00 | 01/17/2030 16:00:00 |  |  |  | Approved | MW | 56 | 56 | 0 | Black Start Demonstration test | integ-mig | 12/31/2023 22:00:00 MST
13779251 | OCOTILLO GT2 | PO | pending | 11/26/2030 00:01:00 | 12/06/2030 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/23/2024 11:38:08 MST
14964307 | OCOTILLO GT2 | PO | pending | 12/02/2031 00:01:00 | 12/12/2031 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned Reliability outage | Z03344 | 10/23/2024 11:38:13 MST
9850339 | PALO VERDE 1 | PO | in_progress | 10/03/2026 00:00:00 | 11/17/2026 23:59:00 |  |  |  | Approved | MW | 1311 | 1311 | 0 | Updated to reflect 2017 Q2 Update outage plan | Z13288 | 10/23/2024 12:45:45 MST
634642 | PALO VERDE 1 | PO | in_progress | 03/25/2028 00:00:00 | 04/29/2028 23:59:00 |  |  |  | Approved | MW | 1311 | 1311 | 0 | Palo Verde 1 refueling outage | Z13288 | 10/17/2025 11:46:49 MST
14501486 | PALO VERDE 1 | PO | in_progress | 10/06/2029 00:00:00 | 11/20/2029 23:59:00 |  |  |  |  | MW | 1311 | 1311 | 0 | Palo Verde 1 refueling outage | Z13288 | 10/23/2024 12:47:00 MST
12078291 | PALO VERDE 1 | PO | in_progress | 03/29/2031 00:00:00 | 05/03/2031 23:59:00 |  |  |  |  | MW | 1311 | 1311 | 0 | Palo Verde 1 refueling outage | Z13288 | 10/23/2024 12:48:07 MST
1070820 | PALO VERDE 2 | PO | in_progress | 10/02/2027 00:00:00 | 11/16/2027 23:59:00 |  |  |  | Approved | MW | 1314 | 1314 | 0 | Palo Verde 2 refueling outage | Z13288 | 10/23/2024 12:52:24 MST
6031844 | PALO VERDE 2 | PO | in_progress | 03/31/2029 00:00:00 | 05/05/2029 23:59:00 |  |  |  |  | MW | 1314 | 1314 | 0 | Palo Verde 2 refueling outage | Z13288 | 10/23/2024 12:52:56 MST
12008039 | PALO VERDE 2 | PO | in_progress | 10/05/2030 00:00:00 | 11/19/2030 23:59:00 |  |  |  |  | MW | 1314 | 1314 | 0 | Palo Verde 2 refueling outage | Z13288 | 10/23/2024 12:53:35 MST
11645257 | PALO VERDE 3 | PO | in_progress | 03/27/2027 00:00:00 | 05/01/2027 23:59:00 |  |  |  | Approved | MW | 1312 | 1312 | 0 | Palo Verde 3 refueling outage | Z13288 | 10/17/2025 13:07:31 MST
458349 | PALO VERDE 3 | PO | in_progress | 10/07/2028 00:00:00 | 11/21/2028 23:59:00 |  |  |  | Approved | MW | 1312 | 1312 | 0 | Palo Verde 3 refueling outage | Z13288 | 10/23/2024 12:56:21 MST
6108510 | PALO VERDE 3 | PO | in_progress | 03/30/2030 00:00:00 | 05/04/2030 23:59:00 |  |  |  |  | MW | 1312 | 1312 | 0 | Palo Verde 3 refueling outage | Z13288 | 10/23/2024 12:57:00 MST
12250265 | PALO VERDE 3 | PO | in_progress | 10/04/2031 00:00:00 | 11/08/2031 23:59:00 |  |  |  |  | MW | 1312 | 1312 | 0 | Palo Verde 3 refueling outage | Z13288 | 10/23/2024 12:57:35 MST
8114380 | PALOMA | PO | in_progress | 03/15/2028 07:00:00 | 03/17/2028 14:00:00 |  |  |  | Approved | MW | 17 | 17 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
12458989 | PALOMA | PO | in_progress | 03/13/2030 07:00:00 | 03/15/2030 14:00:00 |  |  |  | Approved | MW | 17 | 17 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
2228258 | RED ROCK | PO | in_progress | 05/26/2026 08:00:00 | 05/28/2026 14:30:00 |  |  |  |  | MW | 43.9 | 43.9 | 0 | Replacement of 600A disconnect switch with 900A to avoid derating the site. | Z18263 | 05/01/2026 02:49:38 MST
5969343 | RED ROCK | PO | in_progress | 03/12/2029 07:00:00 | 03/19/2029 14:00:00 |  |  |  | Approved | MW | 43.9 | 43.9 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
14496843 | RED ROCK | PO | in_progress | 03/17/2031 07:00:00 | 03/24/2031 14:00:00 |  |  |  | Approved | MW | 43.9 | 43.9 | 0 | Medium voltage inspections | integ-mig | 12/31/2023 22:00:00 MST
12816876 | RED ROCK BESS | PO | in_progress | 05/26/2026 08:00:00 | 05/28/2026 14:30:00 |  |  |  |  | MW | 41 | 41 | 0 | Replacement of 600A disconnect switch with 900A to avoid derating the site. | Z17429 | 05/13/2026 11:07:55 MST
3123940 | REDHAWK CC#1 DB | U1 | in_progress | 12/24/2025 08:20:00 | 05/31/2026 16:00:00 | 12/24/2025 08:20:00 |  |  |  | MW | 550 | 550 | 0 | DB are out of commission ECC has outage in there till 04/03/26 | Z18273 | 04/03/2026 14:22:57 MST
1877601 | REDHAWK CC#2 DB | U1 | in_progress | 05/06/2026 14:50:00 | 05/31/2026 21:20:00 | 05/06/2026 14:50:00 |  |  |  | MW | 13 | 13 | 0 | DB are out of commission ECC has outage in there till 04/03/26 | Z19955 | 05/07/2026 12:21:26 MST
5290886 | REDHAWK CT1 A | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | reliability outage | Z02761 | 04/24/2026 08:15:36 MST
4351561 | REDHAWK CT1 A | PO | in_progress | 11/05/2027 00:01:00 | 12/09/2027 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability outage | Z13288 | 05/11/2026 13:01:22 MST
11963880 | REDHAWK CT1 A | PO | in_progress | 11/02/2028 00:01:00 | 12/04/2028 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | planned outage | Z18263 | 10/28/2024 09:06:08 MST
8286390 | REDHAWK CT1 A | PO | in_progress | 10/27/2029 00:01:00 | 12/12/2029 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | reliability outage | Z13288 | 05/11/2026 13:02:18 MST
13650789 | REDHAWK CT1 A | PO | in_progress | 11/02/2030 00:01:00 | 12/04/2030 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | HGP/Major Outage | Z13288 | 05/11/2026 13:05:53 MST
9235142 | REDHAWK CT1 A | PO | in_progress | 11/01/2031 00:01:00 | 12/05/2031 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | planned outage, HGP and Major on CTs, C inspection on ST1 | integ-mig | 12/31/2023 22:00:00 MST
9725150 | REDHAWK CT1 B | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | reliability outage | Z13288 | 07/21/2025 11:05:21 MST
16560191 | REDHAWK CT1 B | PO | in_progress | 11/05/2027 00:01:00 | 12/09/2027 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability outage | Z13288 | 05/11/2026 13:01:36 MST
5022295 | REDHAWK CT1 B | PO | in_progress | 11/02/2028 00:01:00 | 12/04/2028 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | planned outage | Z18263 | 10/28/2024 09:06:12 MST
15018466 | REDHAWK CT1 B | PO | in_progress | 10/27/2029 00:01:00 | 12/12/2029 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability Outage | Z13288 | 05/11/2026 13:02:21 MST
4827092 | REDHAWK CT1 B | PO | in_progress | 11/02/2030 00:01:00 | 12/04/2030 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | HGP/Major Outage | Z13288 | 05/11/2026 13:05:55 MST
13163760 | REDHAWK CT1 B | PO | in_progress | 11/02/2031 00:01:00 | 12/05/2031 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | planned outage, HGP and Major on CTs, C inspection on ST1 | Z13288 | 10/23/2024 11:23:51 MST
3494890 | REDHAWK CT2 A | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  |  | MW | 180 | 180 | 0 | Fiber optic controller upgrade | Z13288 | 04/27/2026 09:43:50 MST
4719741 | REDHAWK CT2 A | PO | in_progress | 02/27/2027 00:01:00 | 04/21/2027 23:30:00 |  |  |  | Approved | MW | 175 | 175 | 0 | reliability outage | Z13288 | 07/21/2025 11:10:40 MST
10291990 | REDHAWK CT2 A | PO | in_progress | 02/26/2028 00:01:00 | 03/30/2028 23:30:00 |  |  |  | Approved | MW | 179 | 179 | 0 | planned outage HGP / Mjr on CTs | Z18263 | 10/28/2024 09:03:52 MST
1374493 | REDHAWK CT2 A | PO | in_progress | 03/17/2029 00:01:00 | 04/20/2029 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | planned outage unit 2 reliability outage | Z13288 | 05/11/2026 13:04:49 MST
11015623 | REDHAWK CT2 A | PO | in_progress | 03/01/2030 00:01:00 | 04/17/2030 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability Outage unit 2 | Z13288 | 05/11/2026 13:05:18 MST
12572130 | REDHAWK CT2 A | PO | in_progress | 02/22/2031 00:01:00 | 03/31/2031 23:30:00 |  |  |  | Approved | MW | 179 | 179 | 0 | Planned Outage HGP and Major outage on CTs | Z18263 | 10/28/2024 09:04:40 MST
10323243 | REDHAWK CT2 B | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  |  | MW | 180 | 180 | 0 | Fiber optic controller upgrade | Z13288 | 04/27/2026 09:43:53 MST
5295351 | REDHAWK CT2 B | PO | in_progress | 02/27/2027 00:01:00 | 04/21/2027 23:30:00 |  |  |  | Approved | MW | 175 | 175 | 0 | reliablity outage | Z13288 | 07/21/2025 11:09:59 MST
11242699 | REDHAWK CT2 B | PO | in_progress | 02/26/2028 00:01:00 | 03/30/2028 23:30:00 |  |  |  | Approved | MW | 179 | 179 | 0 | planned outages Major and HGP on CTs | Z18263 | 10/28/2024 09:04:05 MST
639293 | REDHAWK CT2 B | PO | in_progress | 03/17/2029 00:01:00 | 04/20/2029 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability outage unit 2 | Z13288 | 05/11/2026 13:04:51 MST
15695249 | REDHAWK CT2 B | PO | in_progress | 03/01/2030 00:01:00 | 04/17/2030 23:30:00 |  |  |  | Approved | MW | 180 | 180 | 0 | Reliability Outage Unit 2 | Z13288 | 05/11/2026 13:05:20 MST
4756883 | REDHAWK CT2 B | PO | in_progress | 02/22/2031 00:01:00 | 03/31/2031 23:30:00 |  |  |  | Approved | MW | 179 | 179 | 0 | planned major and HGP outage | Z18263 | 10/28/2024 09:04:43 MST
14130486 | REDHAWK ST1 | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | ST major C inspection | Z13288 | 02/13/2026 12:47:23 MST
11789882 | REDHAWK ST1 | PO | in_progress | 11/05/2027 00:01:00 | 12/09/2027 23:30:00 |  |  |  | Approved | MW | 177 | 177 | 0 | planned outage | Z13288 | 05/11/2026 13:01:33 MST
11802770 | REDHAWK ST1 | PO | pending | 11/02/2028 00:01:00 | 12/04/2028 23:30:00 |  |  |  |  | MW | 178 | 178 | 0 | planned outage | Z09333 | 10/10/2024 08:26:52 MST
14165612 | REDHAWK ST1 | PO | pending | 10/27/2029 00:01:00 | 12/12/2029 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | reliability outage | Z09333 | 05/08/2026 13:59:45 MST
8447570 | REDHAWK ST1 | PO | pending | 11/02/2030 00:01:00 | 12/04/2030 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | HGP/Major Outage | Z09333 | 05/08/2026 14:05:20 MST
8879335 | REDHAWK ST1 | PO | in_progress | 11/01/2031 00:01:00 | 12/05/2031 23:30:00 |  |  |  | Approved | MW | 177 | 177 | 0 | planned outage, HGP and Major on CTs, C inspection on ST1 | integ-mig | 12/31/2023 22:00:00 MST
5079286 | REDHAWK ST2 | PO | in_progress | 10/31/2026 00:01:00 | 12/23/2026 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | Fiber optic controller upgrade | Z13288 | 04/27/2026 09:43:56 MST
2475618 | REDHAWK ST2 | PO | pending | 02/27/2027 00:01:00 | 04/21/2027 23:30:00 |  |  |  |  | MW | 175 | 175 | 0 | ST major C inspection | Z02761 | 07/22/2025 10:38:06 MST
2830215 | REDHAWK ST2 | PO | in_progress | 02/26/2028 00:01:00 | 03/30/2028 23:30:00 |  |  |  | Approved | MW | 178 | 178 | 0 | planned outage | Z18263 | 10/28/2024 09:04:09 MST
9981013 | REDHAWK ST2 | PO | pending | 03/17/2029 00:01:00 | 04/20/2029 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | planned outage unit 2 reliability outage | Z09333 | 05/08/2026 14:01:24 MST
4992656 | REDHAWK ST2 | PO | pending | 03/02/2030 00:01:00 | 04/17/2030 23:30:00 |  |  |  |  | MW | 177 | 177 | 0 | Reliability Outage unit 2 | Z09333 | 05/08/2026 14:03:37 MST
1609168 | REDHAWK ST2 | PO | in_progress | 02/22/2031 00:01:00 | 03/31/2031 23:30:00 |  |  |  | Approved | MW | 178 | 178 | 0 | planned outage major C inspection ST2 | Z18263 | 10/28/2024 09:04:56 MST
12270674 | SAGUARO CT3 | PE | in_progress | 04/06/2026 18:00:00 | 06/30/2026 18:00:00 | 04/06/2026 18:00:00 |  |  |  | MW | 73 | 73 | 0 | SAC018877 Replace ABB Controller Card BRC and GE HMI, and water wash, compressor blade replacement. SA255799 | Z17429 | 05/13/2026 07:56:50 MST
14364737 | SAGUARO CT3 | PE | in_progress | 12/04/2026 01:00:00 | 12/07/2026 01:00:00 |  |  |  |  | MW | 76 | 76 | 0 | Planned Reliability SA255799 and Combustion inspection outage. SAC016187 | Z13288 | 04/17/2026 08:35:02 MST
16015552 | SAGUARO CT3 | PO | in_progress | 12/07/2026 01:00:00 | 12/21/2026 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | Planned Reliability SA255799 and Combustion inspection outage. SAC016187 | Z13288 | 10/13/2025 13:17:41 MST
9353679 | SAGUARO CT3 | PE | in_progress | 12/21/2026 23:59:00 | 12/24/2026 18:00:00 |  |  |  |  | MW | 76 | 76 | 0 | Planned Reliability SA255799 and Combustion inspection outage. SAC016187 | Z13288 | 04/17/2026 08:35:12 MST
1310571 | SAGUARO CT3 | PO | pending | 12/04/2027 01:00:00 | 12/13/2027 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | Reliability outage SA255739 | Z05860 | 06/26/2025 06:12:58 MST
5815558 | SAGUARO CT3 | PO | pending | 12/03/2028 01:00:00 | 12/28/2028 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | Planned outage Combustion inspection SAC016188 | Z03343 | 03/12/2025 12:55:30 MST
1985772 | SAGUARO CT3 | PO | pending | 12/08/2029 01:00:00 | 12/17/2029 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | Reliability outage. | Z03343 | 03/12/2025 12:57:50 MST
13808908 | SAGUARO CT3 | PO | pending | 12/07/2030 01:00:00 | 12/21/2030 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | SA3 planned outage Hot Gas Path SAC016190 | Z03343 | 03/12/2025 13:05:31 MST
293090 | SAGUARO CT3 | PO | pending | 01/06/2031 01:00:00 | 01/27/2031 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | SA3 Planned outage Combustion inspection SAC015491 | Z03343 | 03/12/2025 13:20:48 MST
15127858 | SAGUARO CT3 | PO | pending | 12/06/2031 01:00:00 | 12/15/2031 23:59:00 |  |  |  |  | MW | 76 | 76 | 0 | Reliability outage. | Z03343 | 03/12/2025 12:58:39 MST
458913 | SAGUARO GT1 | PO | in_progress | 10/05/2026 01:00:00 | 12/04/2026 18:00:00 |  |  |  |  | MW | 50 | 50 | 0 | SA1 Planned outage Major SAC015489 | Z13288 | 10/14/2025 07:55:41 MST
7586328 | SAGUARO GT1 | PO | in_progress | 01/05/2027 00:01:00 | 01/15/2027 23:59:00 |  |  |  | Approved | MW | 56 | 56 | 0 | Reliability outage. | Z18263 | 10/28/2024 09:06:59 MST
11317006 | SAGUARO GT1 | PO | pending | 01/05/2027 00:01:00 | 01/15/2027 23:59:00 |  |  |  |  | MW | 56 | 0 | 0 | Reliability outage SA255644 | Z05860 | 06/26/2025 06:06:52 MST
376678 | SAGUARO GT1 | PO | pending | 01/03/2028 00:01:00 | 01/13/2028 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Reliability outage. | Z03343 | 03/12/2025 13:32:05 MST
2826063 | SAGUARO GT1 | PO | pending | 01/08/2029 00:01:00 | 01/18/2029 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Reliability outage. | Z03343 | 03/12/2025 13:33:20 MST
4972881 | SAGUARO GT1 | PO | pending | 01/08/2030 00:01:00 | 01/18/2030 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Reliability outage. | Z03343 | 03/12/2025 13:33:52 MST
5904450 | SAGUARO GT1 | PO | pending | 01/06/2031 00:01:00 | 01/16/2031 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Reliability outage. | Z03344 | 10/22/2024 10:12:25 MST
8789814 | SAGUARO GT1 | PO | pending | 01/06/2031 01:00:00 | 01/27/2031 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Reliability outage | Z03343 | 03/12/2025 13:35:13 MST
12624735 | SAGUARO GT2 | U1 | in_progress | 05/20/2026 17:55:00 | 05/21/2026 20:00:00 | 05/20/2026 17:55:00 | 05/21/2026 20:00:00 |  |  | MW | 50 | 50 | 0 | SA GT2 test run was unsuccessful due to Net MW output. | Z18937 | 05/21/2026 20:00:25 MST
10540823 | SAGUARO GT2 | PO | in_progress | 03/09/2027 00:01:00 | 03/29/2027 18:00:00 |  |  |  |  | MW | 55 | 55 | 0 | Reliability outage SA255870 and combustion inspection. | Z13288 | 08/12/2025 09:46:55 MST
3333009 | SAGUARO GT2 | PO | pending | 03/07/2028 00:01:00 | 03/17/2028 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | Reliability outage and expansion joint. | Z05860 | 09/03/2025 09:22:54 MST
6247351 | SAGUARO GT2 | PO | pending | 03/06/2029 00:01:00 | 03/16/2029 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | Reliability outage. | Z03344 | 10/22/2024 10:36:30 MST
6130856 | SAGUARO GT2 | PO | pending | 03/05/2030 00:01:00 | 03/15/2030 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | Reliability outage. | Z03344 | 10/22/2024 10:36:47 MST
1681364 | SAGUARO GT2 | PO | pending | 03/04/2031 00:01:00 | 03/14/2031 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | Reliability outage. | Z03344 | 10/22/2024 10:36:49 MST
7208984 | SAGUARO GT2 | PO | pending | 12/06/2031 01:00:00 | 12/20/2031 23:59:00 |  |  |  |  | MW | 56 | 56 | 0 | Planned outage Combustion Inspection SAC015490 | Z03343 | 03/12/2025 13:59:34 MST
5561068 | SNOWFLAKE BIOMASS | MO | in_progress | 05/26/2026 06:00:00 | 05/29/2026 06:00:00 |  |  |  |  | MW | 14 | 14 | 0 | Maintenance outage requested for Snowflake | Z13288 | 04/29/2026 11:59:13 MST
16057716 | SOUTH POINT CC DB+PA | U1 | in_progress | 05/08/2026 15:00:00 | 05/31/2026 23:59:00 | 05/08/2026 15:00:00 |  |  |  | MW | 463 | 463 | 0 | Unavailable due to rotor repairs | Z18937 | 05/11/2026 10:58:30 MST
6873954 | SOUTH POINT CC DB+PA | PO | in_progress | 10/31/2026 23:59:00 | 04/30/2027 23:59:00 |  |  |  |  | MW | 463 | 463 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:03 MST
16578811 | SOUTH POINT CC DB+PA | PO | in_progress | 10/31/2027 23:59:00 | 04/30/2028 23:59:00 |  |  |  |  | MW | 463 | 463 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:46 MST
9167880 | SOUTH POINT CC DB+PA | PO | in_progress | 10/31/2028 23:59:00 | 04/30/2029 23:59:00 |  |  |  |  | MW | 463 | 463 | 0 | Unit out of season | Z13288 | 10/23/2024 13:28:37 MST
36811 | SOUTH POINT CC DB+PA | PO | in_progress | 10/31/2029 23:59:00 | 04/30/2030 23:59:00 |  |  |  |  | MW | 463 | 463 | 0 | Unit out of season | Z13288 | 10/23/2024 13:29:26 MST
105385 | SOUTH POINT CTA | U1 | in_progress | 05/01/2026 14:00:00 | 05/31/2026 23:59:00 | 05/01/2026 14:00:00 |  |  |  | MW | 154 | 154 | 0 | South point having issues with steam turbin, unit is not able to reach 1x1, expecting update monday may 4 | Z13288 | 05/11/2026 10:58:48 MST
10631684 | SOUTH POINT CTA | PO | in_progress | 10/31/2026 23:59:00 | 04/30/2027 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:12 MST
2415265 | SOUTH POINT CTA | PO | in_progress | 10/31/2027 23:59:00 | 04/30/2028 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:55 MST
5852358 | SOUTH POINT CTA | PO | in_progress | 10/31/2028 23:59:00 | 04/30/2029 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:28:44 MST
6148813 | SOUTH POINT CTA | PO | in_progress | 10/31/2029 23:59:00 | 04/30/2030 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:29:35 MST
10532072 | SOUTH POINT CTB | U1 | in_progress | 05/01/2026 14:00:00 | 05/31/2026 23:59:00 | 05/01/2026 14:00:00 |  |  |  | MW | 154 | 154 | 0 | South point having issues with Steam Turbine, wont be able to make it into a 1x1 expecting update monday 4 | Z13288 | 05/11/2026 10:58:58 MST
9913216 | SOUTH POINT CTB | PO | in_progress | 10/31/2026 23:59:00 | 04/30/2027 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:19 MST
6245210 | SOUTH POINT CTB | PO | in_progress | 10/31/2027 23:59:00 | 04/30/2028 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:28:04 MST
4399898 | SOUTH POINT CTB | PO | in_progress | 10/31/2028 23:59:00 | 04/30/2029 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:28:54 MST
14033548 | SOUTH POINT CTB | PO | in_progress | 10/31/2029 23:59:00 | 04/30/2030 23:59:00 |  |  |  |  | MW | 154 | 154 | 0 | Unit out of season | Z13288 | 10/23/2024 13:29:43 MST
11432429 | SOUTH POINT ST | U1 | in_progress | 05/08/2026 15:00:00 | 05/31/2026 23:59:00 | 05/08/2026 15:00:00 |  |  |  | MW | 170 | 170 | 0 | Unavailable due to rotor repairs | Z18937 | 05/11/2026 10:58:56 MST
14932103 | SOUTH POINT ST | PO | in_progress | 10/31/2026 23:59:00 | 04/30/2027 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:26:54 MST
15174474 | SOUTH POINT ST | PO | in_progress | 10/31/2027 23:59:00 | 04/30/2028 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:27:37 MST
8741643 | SOUTH POINT ST | PO | in_progress | 10/31/2028 23:59:00 | 04/30/2029 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:28:25 MST
1547347 | SOUTH POINT ST | PO | in_progress | 10/31/2029 23:59:00 | 04/30/2030 23:59:00 |  |  |  |  | MW | 170 | 170 | 0 | Unit out of season | Z13288 | 10/23/2024 13:29:16 MST
5791536 | SUN STREAMS 4 SOLAR | MO | in_progress | 05/20/2026 20:30:00 | 05/21/2026 05:00:00 | 05/20/2026 20:30:00 | 05/21/2026 05:00:00 |  |  | MW | 300 | 300 | 0 | Outage needed for GSU maintenance | Z18937 | 05/21/2026 05:00:36 MST
4182984 | SUN STREAMS 4 SOLAR | MO | in_progress | 05/21/2026 20:30:00 | 05/21/2026 21:25:00 | 05/21/2026 20:30:00 | 05/21/2026 20:31:00 |  |  | MW | 300 | 300 | 0 | Outage needed for GSU maintenance | Z18273 | 05/21/2026 21:25:28 MST
2545560 | SUNDANCE 1 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 18:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Fuel nozzle replacement to correct T48 temperature spread. | Z18263 | 05/15/2026 07:08:17 MST
3247396 | SUNDANCE 1 CT | MO | in_progress | 05/27/2026 18:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:22:23 MST
4445949 | SUNDANCE 1 CT | PO | in_progress | 10/14/2026 01:00:00 | 10/29/2026 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage SD295561 | Z05860 | 06/26/2025 06:04:26 MST
2742921 | SUNDANCE 1 CT | PO | in_progress | 10/13/2027 01:00:00 | 10/28/2027 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage SD295329 | Z05860 | 06/26/2025 06:10:58 MST
3022412 | SUNDANCE 1 CT | PO | in_progress | 10/11/2028 01:00:00 | 10/26/2028 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
14700900 | SUNDANCE 1 CT | PO | in_progress | 10/10/2029 01:00:00 | 10/25/2029 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
4138980 | SUNDANCE 1 CT | PO | in_progress | 10/09/2030 01:00:00 | 10/24/2030 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
16228076 | SUNDANCE 1 CT | PO | in_progress | 10/15/2031 01:00:00 | 10/30/2031 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
8886637 | SUNDANCE 10 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:19:52 MST
13950041 | SUNDANCE 10 CT | PO | in_progress | 02/24/2027 01:00:00 | 03/11/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage SD295064 | Z05860 | 06/26/2025 06:11:19 MST
16373693 | SUNDANCE 10 CT | PO | in_progress | 02/23/2028 01:00:00 | 03/09/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
16414493 | SUNDANCE 10 CT | PO | in_progress | 02/28/2029 01:00:00 | 03/15/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
1379499 | SUNDANCE 10 CT | PO | in_progress | 02/27/2030 01:00:00 | 03/14/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
6207791 | SUNDANCE 10 CT | PO | in_progress | 02/26/2031 01:00:00 | 03/13/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
16250762 | SUNDANCE 11 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:22:05 MST
4419655 | SUNDANCE 11 CT | PO | in_progress | 11/30/2026 01:00:00 | 12/14/2026 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z13288 | 12/29/2025 12:31:24 MST
6716720 | SUNDANCE 11 CT | PO | pending | 11/29/2027 01:00:00 | 12/13/2027 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:50:35 MST
1819435 | SUNDANCE 11 CT | PO | pending | 11/20/2028 01:00:00 | 12/22/2028 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage and Relay Replacement project | Z05860 | 02/03/2026 23:53:14 MST
6401734 | SUNDANCE 11 CT | PO | pending | 11/26/2029 01:00:00 | 12/10/2029 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:56:44 MST
16166664 | SUNDANCE 11 CT | PO | pending | 11/25/2030 01:00:00 | 12/09/2030 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:58:41 MST
1675813 | SUNDANCE 11 CT | PO | pending | 12/01/2031 01:00:00 | 12/16/2031 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/04/2026 00:00:41 MST
7213974 | SUNDANCE 12 CT | MO | in_progress | 05/27/2026 06:00:00 | 05/28/2026 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | SD12 Dilution air fan "A" replacement. | Z18263 | 05/01/2026 06:28:16 MST
181191 | SUNDANCE 12 CT | PO | in_progress | 11/30/2026 01:00:00 | 12/14/2026 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z13288 | 12/29/2025 12:31:27 MST
13023462 | SUNDANCE 12 CT | PO | pending | 11/29/2027 01:00:00 | 12/13/2027 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:51:14 MST
15883014 | SUNDANCE 12 CT | PO | pending | 11/20/2028 01:00:00 | 12/22/2028 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage and Relay Replacement project | Z05860 | 02/03/2026 23:53:57 MST
12020176 | SUNDANCE 12 CT | PO | pending | 11/26/2029 01:00:00 | 12/10/2029 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:56:34 MST
11933693 | SUNDANCE 12 CT | PO | pending | 11/25/2030 01:00:00 | 12/09/2030 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/03/2026 23:59:11 MST
15738335 | SUNDANCE 12 CT | PO | pending | 12/01/2031 01:00:00 | 12/16/2031 18:00:00 |  |  |  |  | MW | 45 | 45 | 0 | Sundance Power Block 6 Planned Unit Outage | Z05860 | 02/04/2026 00:01:22 MST
8635732 | SUNDANCE 2 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:19:46 MST
4747382 | SUNDANCE 2 CT | PO | in_progress | 10/14/2026 01:00:00 | 10/29/2026 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage SD295561 | Z05860 | 06/26/2025 06:04:42 MST
3354492 | SUNDANCE 2 CT | PO | in_progress | 10/13/2027 01:00:00 | 10/28/2027 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage SD295329 | Z05860 | 06/26/2025 06:11:10 MST
1335155 | SUNDANCE 2 CT | PO | in_progress | 10/11/2028 01:00:00 | 10/26/2028 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
5451851 | SUNDANCE 2 CT | PO | in_progress | 10/10/2029 01:00:00 | 10/25/2029 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
5136369 | SUNDANCE 2 CT | PO | in_progress | 10/09/2030 01:00:00 | 10/24/2030 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
1027755 | SUNDANCE 2 CT | PO | in_progress | 10/15/2031 01:00:00 | 10/30/2031 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 1 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
8431914 | SUNDANCE 3 CT | U1 | in_progress | 04/30/2026 16:45:00 | 06/01/2026 23:59:00 | 04/30/2026 16:00:00 |  |  |  | MW | 42 | 42 | 0 | Offline due to excessive smoke venting from the turbine compartment, CRF oil leak identified. | Z17267 | 05/10/2026 00:35:45 MST
7734405 | SUNDANCE 3 CT | PO | in_progress | 11/04/2026 01:00:00 | 11/19/2026 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 1 Planned Unit Outage SD295677 | Z05860 | 06/26/2025 06:05:12 MST
7223645 | SUNDANCE 3 CT | PO | in_progress | 11/03/2027 01:00:00 | 11/18/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage SD295443 | Z05860 | 06/26/2025 06:12:24 MST
12813517 | SUNDANCE 3 CT | PO | in_progress | 11/01/2028 01:00:00 | 11/16/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
7080549 | SUNDANCE 3 CT | PO | in_progress | 10/31/2029 01:00:00 | 11/15/2029 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
5392841 | SUNDANCE 3 CT | PO | in_progress | 10/30/2030 01:00:00 | 11/14/2030 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
14782789 | SUNDANCE 3 CT | PO | in_progress | 11/05/2031 01:00:00 | 11/20/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
11929293 | SUNDANCE 4 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:21:52 MST
7279364 | SUNDANCE 4 CT | MO | canceled | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:16:36 MST
15869466 | SUNDANCE 4 CT | PO | in_progress | 11/04/2026 01:00:00 | 11/19/2026 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 1 Planned Unit Outage SD295677 | Z05860 | 06/26/2025 06:05:24 MST
7114332 | SUNDANCE 4 CT | PO | in_progress | 11/03/2027 01:00:00 | 11/18/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage SD295443 | Z05860 | 06/26/2025 06:12:36 MST
13209256 | SUNDANCE 4 CT | PO | in_progress | 11/01/2028 01:00:00 | 11/16/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
6071729 | SUNDANCE 4 CT | PO | in_progress | 10/31/2029 01:00:00 | 11/15/2029 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
10672767 | SUNDANCE 4 CT | PO | in_progress | 10/30/2030 01:00:00 | 11/14/2030 18:00:00 |  |  |  | Approved | MW | 40 | 40 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
138426 | SUNDANCE 4 CT | PO | in_progress | 11/05/2031 01:00:00 | 11/20/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 2 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
14324716 | SUNDANCE 5 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:21:46 MST
8832171 | SUNDANCE 5 CT | PO | in_progress | 01/13/2027 01:00:00 | 01/28/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage SD294829 | Z05860 | 06/26/2025 06:08:07 MST
8632604 | SUNDANCE 5 CT | PO | in_progress | 01/12/2028 01:00:00 | 01/27/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
4260361 | SUNDANCE 5 CT | PO | in_progress | 01/17/2029 01:00:00 | 02/01/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
10523251 | SUNDANCE 5 CT | PO | in_progress | 01/16/2030 01:00:00 | 01/31/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
1482312 | SUNDANCE 5 CT | PO | in_progress | 01/15/2031 01:00:00 | 01/30/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
11555934 | SUNDANCE 6 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:20:04 MST
4873294 | SUNDANCE 6 CT | PO | in_progress | 01/13/2027 01:00:00 | 01/28/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage SD294829 | Z05860 | 06/26/2025 06:08:24 MST
2358324 | SUNDANCE 6 CT | PO | in_progress | 01/12/2028 01:00:00 | 01/27/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
7467458 | SUNDANCE 6 CT | PO | in_progress | 01/17/2029 01:00:00 | 02/01/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
2808185 | SUNDANCE 6 CT | PO | in_progress | 01/16/2030 01:00:00 | 01/31/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
12042813 | SUNDANCE 6 CT | PO | in_progress | 01/15/2031 01:00:00 | 01/30/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 3 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
5485703 | SUNDANCE 7 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:21:42 MST
5215371 | SUNDANCE 7 CT | PO | in_progress | 02/03/2027 01:00:00 | 02/18/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage SD294943 | Z05860 | 06/26/2025 06:08:59 MST
11420217 | SUNDANCE 7 CT | PO | in_progress | 02/02/2028 01:00:00 | 02/17/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
13969325 | SUNDANCE 7 CT | PO | in_progress | 02/07/2029 01:00:00 | 02/22/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
3612197 | SUNDANCE 7 CT | PO | in_progress | 02/06/2030 01:00:00 | 02/21/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
2138895 | SUNDANCE 7 CT | PO | in_progress | 02/05/2031 01:00:00 | 02/20/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
12473679 | SUNDANCE 8 CT | MO | in_progress | 05/21/2026 07:00:00 | 05/21/2026 15:45:00 | 05/21/2026 07:00:00 | 05/21/2026 15:08:00 |  |  | MW | 40 | 40 | 0 | MO to replace combustion filter cartridges. | Z19944 | 05/21/2026 15:46:14 MST
12627463 | SUNDANCE 8 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:21:36 MST
3725684 | SUNDANCE 8 CT | PO | in_progress | 02/03/2027 01:00:00 | 02/18/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage SD294943 | Z05860 | 07/31/2025 08:59:20 MST
3383649 | SUNDANCE 8 CT | PO | in_progress | 02/02/2028 01:00:00 | 02/17/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | Z05860 | 07/31/2025 08:59:11 MST
3481056 | SUNDANCE 8 CT | PO | in_progress | 02/07/2029 01:00:00 | 02/22/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | Z05860 | 07/31/2025 08:58:55 MST
13961851 | SUNDANCE 8 CT | PO | in_progress | 02/06/2030 01:00:00 | 02/21/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
3411991 | SUNDANCE 8 CT | PO | in_progress | 02/05/2031 01:00:00 | 02/20/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 4 Planned Unit Outage (Ten Year Schedule) | Z05860 | 07/31/2025 08:58:41 MST
2451492 | SUNDANCE 9 CT | MO | in_progress | 05/27/2026 07:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 40 | 40 | 0 | Plant wide Sundance outage to complete gas line PM and maintenance. | Z18263 | 05/19/2026 12:20:44 MST
12058926 | SUNDANCE 9 CT | PO | in_progress | 02/24/2027 01:00:00 | 03/11/2027 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage SD295064 | Z05860 | 06/26/2025 06:11:26 MST
15386788 | SUNDANCE 9 CT | PO | in_progress | 02/23/2028 01:00:00 | 03/09/2028 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
14631085 | SUNDANCE 9 CT | PO | in_progress | 02/28/2029 01:00:00 | 03/15/2029 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
9890495 | SUNDANCE 9 CT | PO | in_progress | 02/27/2030 01:00:00 | 03/14/2030 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
2573309 | SUNDANCE 9 CT | PO | in_progress | 02/26/2031 01:00:00 | 03/13/2031 18:00:00 |  |  |  | Approved | MW | 43 | 43 | 0 | Sundance Power Block 5 Planned Unit Outage (Ten Year Schedule) | integ-mig | 12/31/2023 22:00:00 MST
4129431 | WEST PHOENIX CC#4 ST | MO | pending | 10/20/2026 06:00:00 | 10/21/2026 18:00:00 |  |  |  |  | MW | 34 | 34 | 0 | CC4 Post summer run steam turbine oil filter change. | Z11296 | 12/23/2025 10:51:38 MST
1980409 | WEST PHOENIX CC1 | MO | in_progress | 05/18/2026 00:01:00 | 05/22/2026 18:00:00 | 05/18/2026 00:01:00 |  |  |  | MW | 85 | 85 | 0 | CC1 summer prep outage to change Munters fill and any other routine maintenance. | Z18273 | 05/21/2026 18:01:39 MST
6699728 | WEST PHOENIX CC1 | PO | in_progress | 10/03/2026 00:01:00 | 10/30/2026 23:59:00 |  |  |  |  | MW | 85 | 85 | 0 | CC12 Relay Replacement Project and Fuel Gas Regulator Station Replacement Project | Z13288 | 04/08/2026 10:28:53 MST
13815369 | WEST PHOENIX CC1 | PO | in_progress | 01/30/2027 00:01:00 | 02/14/2027 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:14:53 MST
10275635 | WEST PHOENIX CC1 | PO | in_progress | 01/29/2028 00:01:00 | 02/13/2028 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Combustion Inspection | Z13288 | 12/19/2025 07:15:16 MST
16278348 | WEST PHOENIX CC1 | PO | in_progress | 01/27/2029 00:01:00 | 02/11/2029 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:15:38 MST
14462543 | WEST PHOENIX CC1 | PO | in_progress | 01/26/2030 00:01:00 | 02/10/2030 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Hot Gas Path Inspection | Z13288 | 12/19/2025 07:16:47 MST
8404267 | WEST PHOENIX CC1 | PO | in_progress | 01/25/2031 00:01:00 | 02/16/2031 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:17:16 MST
6106164 | WEST PHOENIX CC2 | PO | in_progress | 10/03/2026 00:01:00 | 10/30/2026 23:59:00 |  |  |  |  | MW | 85 | 85 | 0 | CC12 Relay Replacement Project and Fuel Gas Regulator Station Replacement Project | Z13288 | 04/08/2026 10:29:00 MST
14005947 | WEST PHOENIX CC2 | PO | pending | 10/03/2026 00:01:00 | 10/16/2026 23:59:00 |  |  |  |  | MW | 85 | 85 | 0 | Reliability Outage | Z05865 | 01/05/2026 10:37:18 MST
4432016 | WEST PHOENIX CC2 | PO | in_progress | 10/30/2027 00:01:00 | 11/12/2027 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:46:57 MST
53198 | WEST PHOENIX CC2 | PO | in_progress | 10/21/2028 00:01:00 | 11/17/2028 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Hot Gas Path | Z13288 | 10/17/2025 14:47:18 MST
12654643 | WEST PHOENIX CC2 | PO | in_progress | 10/06/2029 00:01:00 | 10/19/2029 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:47:39 MST
6783296 | WEST PHOENIX CC2 | PO | in_progress | 11/02/2030 00:01:00 | 11/15/2030 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Combustion Inspection | Z13288 | 10/17/2025 14:47:56 MST
1537244 | WEST PHOENIX CC2 | PO | in_progress | 11/01/2031 00:01:00 | 11/14/2031 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:48:20 MST
8432030 | WEST PHOENIX CC3 | MO | in_progress | 05/26/2026 19:00:00 | 05/27/2026 19:00:00 |  |  |  |  | MW | 85 | 85 | 0 | Maintenance outage to replace DC Lube Oil Pump. | Z18263 | 05/20/2026 11:46:18 MST
14272908 | WEST PHOENIX CC3 | PO | in_progress | 10/03/2026 00:01:00 | 10/30/2026 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + CC12 Relay Replacement Project & Fuel Gas Regulator Station Replacement Project | Z13288 | 04/07/2026 09:36:05 MST
4022861 | WEST PHOENIX CC3 | PO | in_progress | 10/02/2027 00:01:00 | 11/18/2027 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Major Inspection | Z13288 | 10/17/2025 14:49:21 MST
39796 | WEST PHOENIX CC3 | PO | in_progress | 10/07/2028 00:01:00 | 10/23/2028 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:49:55 MST
949109 | WEST PHOENIX CC3 | PO | pending | 11/03/2029 00:01:00 | 11/16/2029 23:59:00 |  |  |  |  | MW | 85 | 85 | 0 | Reliability Outage + Combustion Inspection | Z03344 | 10/28/2024 10:07:58 MST
4601289 | WEST PHOENIX CC3 | PO | in_progress | 10/05/2030 00:01:00 | 10/18/2030 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:50:29 MST
16603147 | WEST PHOENIX CC3 | PO | in_progress | 10/04/2031 00:01:00 | 10/28/2031 23:59:00 |  |  |  | Approved | MW | 85 | 85 | 0 | Reliability Outage + Hot Gas Path Inspection | Z13288 | 10/17/2025 14:50:50 MST
11565831 | WEST PHOENIX CT5A | PO | in_progress | 01/09/2027 00:01:00 | 02/02/2027 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:20:11 MST
8801417 | WEST PHOENIX CT5A | PO | in_progress | 01/08/2028 00:01:00 | 02/01/2028 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:15 MST
8042148 | WEST PHOENIX CT5A | PO | canceled | 10/07/2028 00:01:00 | 11/26/2028 23:59:00 |  |  |  | Approved | MW | 171 | 171 | 0 | Major Inspection | Z18263 | 10/28/2024 10:08:44 MST
4247347 | WEST PHOENIX CT5A | PO | in_progress | 01/13/2029 00:01:00 | 02/06/2029 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:54 MST
2155001 | WEST PHOENIX CT5A | PO | in_progress | 01/12/2030 00:01:00 | 02/05/2030 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:23:31 MST
4438300 | WEST PHOENIX CT5A | PO | in_progress | 01/11/2031 00:01:00 | 02/04/2031 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage + Hot Gas Path Inspection | Z05865 | 10/28/2024 09:53:43 MST
10710622 | WEST PHOENIX CT5B | U1 | in_progress | 05/18/2026 04:10:00 | 05/22/2026 08:00:00 | 05/18/2026 03:00:00 | 05/22/2026 08:00:00 |  |  | MW | 171 | 171 | 0 | West Phoenix CC5B unavailable in forced outage at 0300 due to Boiler Feed Pump failure to start. Troubleshooting in progress. Update to be provided by 5/18 at 1200. | Z17513 | 05/22/2026 08:00:40 MST
7333161 | WEST PHOENIX CT5B | PO | in_progress | 01/09/2027 00:01:00 | 02/02/2027 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:19:53 MST
12195845 | WEST PHOENIX CT5B | PO | in_progress | 01/08/2028 00:01:00 | 02/01/2028 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:11 MST
15888882 | WEST PHOENIX CT5B | PO | in_progress | 01/13/2029 00:01:00 | 02/06/2029 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:51 MST
14089826 | WEST PHOENIX CT5B | PO | in_progress | 01/12/2030 00:01:00 | 02/05/2030 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:23:27 MST
5579357 | WEST PHOENIX CT5B | PO | in_progress | 01/11/2031 00:01:00 | 02/04/2031 23:59:00 |  |  |  | Approved | MW | 175 | 175 | 0 | Reliability Outage + Hot Gas Path Inspection | Z18263 | 10/28/2024 15:50:07 MST
6515985 | WEST PHOENIX CXC4 | PO | in_progress | 03/07/2026 00:01:00 | 05/23/2026 18:00:00 | 03/07/2026 00:01:00 |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage + Major Inspection | Z17267 | 05/21/2026 17:46:02 MST
685508 | WEST PHOENIX CXC4 | PO | in_progress | 03/06/2027 00:01:00 | 03/19/2027 23:59:00 |  |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage | Z13288 | 10/02/2025 07:50:25 MST
15332119 | WEST PHOENIX CXC4 | PO | in_progress | 03/04/2028 00:01:00 | 03/17/2028 23:59:00 |  |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage + Combustion Inspection | Z13288 | 10/02/2025 07:50:36 MST
12909695 | WEST PHOENIX CXC4 | PO | in_progress | 03/03/2029 00:01:00 | 03/16/2029 23:59:00 |  |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage | Z18263 | 10/28/2024 15:51:53 MST
6222362 | WEST PHOENIX CXC4 | PO | in_progress | 03/16/2030 00:01:00 | 04/12/2030 23:59:00 |  |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage + Hot Gas Path Inspection | Z13288 | 10/02/2025 07:51:40 MST
11237849 | WEST PHOENIX CXC4 | PO | in_progress | 03/08/2031 00:01:00 | 03/21/2031 23:59:00 |  |  |  | Approved | MW | 108 | 108 | 0 | Reliability Outage | Z13288 | 10/02/2025 07:51:58 MST
34342 | WEST PHOENIX GT1 | PO | in_progress | 10/03/2026 00:01:00 | 10/30/2026 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | CC12 Relay Replacement Project and Fuel Gas Regulator Station Replacement Project | Z13288 | 04/08/2026 10:28:35 MST
3838609 | WEST PHOENIX GT1 | PO | in_progress | 12/05/2026 00:01:00 | 12/18/2026 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 04/08/2026 08:01:01 MST
7914236 | WEST PHOENIX GT1 | PO | in_progress | 12/04/2027 00:01:00 | 12/17/2027 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:16:32 MST
6889171 | WEST PHOENIX GT1 | PO | in_progress | 12/02/2028 00:01:00 | 12/15/2028 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:17:42 MST
2873113 | WEST PHOENIX GT1 | PO | in_progress | 12/01/2029 00:01:00 | 12/14/2029 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:18:10 MST
3437161 | WEST PHOENIX GT1 | PO | in_progress | 11/30/2030 00:01:00 | 12/13/2030 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:19:06 MST
9927070 | WEST PHOENIX GT1 | PO | in_progress | 11/23/2031 00:01:00 | 12/17/2031 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage + Hot Gas Path Inspection | Z13288 | 10/17/2025 14:20:31 MST
951209 | WEST PHOENIX GT2 | PO | in_progress | 10/03/2026 00:01:00 | 10/30/2026 23:59:00 |  |  |  |  | MW | 55 | 55 | 0 | CC12 Relay Replacement Project and Fuel Gas Regulator Station Replacement Project | Z13288 | 04/08/2026 10:28:44 MST
351566 | WEST PHOENIX GT2 | PO | in_progress | 12/05/2026 00:01:00 | 12/18/2026 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 01/06/2026 09:08:44 MST
3259547 | WEST PHOENIX GT2 | PO | pending | 12/04/2027 00:01:00 | 12/17/2027 23:59:00 |  |  |  |  | MW | 57 | 57 | 0 | Reliability Outage | Z05865 | 10/15/2025 14:07:35 MST
9642458 | WEST PHOENIX GT2 | PO | in_progress | 12/02/2028 00:01:00 | 12/15/2028 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:17:16 MST
2806694 | WEST PHOENIX GT2 | PO | in_progress | 12/01/2029 00:01:00 | 12/14/2029 23:59:00 |  |  |  | Approved | MW | 57 | 57 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:18:32 MST
3400070 | WEST PHOENIX GT2 | PO | in_progress | 11/30/2030 00:01:00 | 12/13/2030 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:19:02 MST
5098842 | WEST PHOENIX GT2 | PO | in_progress | 11/23/2031 00:01:00 | 12/06/2031 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | Z13288 | 10/17/2025 14:20:27 MST
10944816 | WEST PHOENIX ST5 | U1 | in_progress | 05/18/2026 04:45:00 | 05/22/2026 08:00:00 | 05/18/2026 03:30:00 | 05/22/2026 08:00:00 |  |  | MW | 154 | 154 | 0 | West Phoenix ST 5 failed to start and is unavailable due to Steam Turbine rotor lockup. 5A was taken offline and is unavailable due to ST. An update on Return to Service will be provided by 5/18 at 1200. | Z17513 | 05/22/2026 08:00:37 MST
107509 | WEST PHOENIX ST5 | PO | in_progress | 01/09/2027 00:01:00 | 02/02/2027 23:59:00 |  |  |  | Approved | MW | 157 | 157 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:20:25 MST
8194425 | WEST PHOENIX ST5 | PO | in_progress | 01/08/2028 00:01:00 | 02/01/2028 23:59:00 |  |  |  | Approved | MW | 157 | 157 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:19 MST
10142753 | WEST PHOENIX ST5 | PO | in_progress | 01/13/2029 00:01:00 | 02/06/2029 23:59:00 |  |  |  | Approved | MW | 157 | 157 | 0 | Reliability Outage | Z13288 | 12/19/2025 07:22:59 MST
15222190 | WEST PHOENIX ST5 | PO | in_progress | 01/12/2030 00:01:00 | 02/05/2030 23:59:00 |  |  |  | Approved | MW | 157 | 157 | 0 | Reliability Outage + 25K Inspection | Z13288 | 12/19/2025 07:23:40 MST
3490108 | WEST PHOENIX ST5 | PO | in_progress | 01/11/2031 00:01:00 | 02/04/2031 23:59:00 |  |  |  | Approved | MW | 157 | 157 | 0 | Reliability Outage | Z05865 | 09/29/2025 11:14:58 MST
12281111 | WEST WING I BESS | PO | in_progress | 10/22/2026 19:00:00 | 10/23/2026 05:00:00 |  |  |  |  | MW | 80 | 80 | 0 | Planned outage requested | Z13288 | 04/07/2026 08:58:02 MST
11584275 | WEST WING II BESS | PO | in_progress | 10/22/2026 19:00:00 | 10/23/2026 05:00:00 |  |  |  |  | MW | 120 | 120 | 0 | Planned outage requested | Z13288 | 04/07/2026 08:58:12 MST
8172498 | YUCCA GT1 | PO | in_progress | 01/04/2027 00:01:00 | 01/15/2027 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7618098 | YUCCA GT1 | PO | in_progress | 01/10/2028 00:01:00 | 01/21/2028 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
8280941 | YUCCA GT1 | PO | in_progress | 01/08/2029 00:01:00 | 01/19/2029 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
6214361 | YUCCA GT1 | PO | in_progress | 01/07/2030 00:01:00 | 01/18/2030 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1884360 | YUCCA GT1 | PO | in_progress | 01/06/2031 00:01:00 | 01/17/2031 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
13288141 | YUCCA GT2 | PO | in_progress | 01/18/2027 00:01:00 | 03/05/2027 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Unit Reliability and generator rotor rewind (Capital). | Z13288 | 07/08/2025 09:24:35 MST
14613566 | YUCCA GT2 | PO | in_progress | 01/24/2028 00:01:00 | 02/04/2028 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
9943112 | YUCCA GT2 | PO | in_progress | 01/22/2029 00:01:00 | 02/02/2029 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
2823964 | YUCCA GT2 | PO | in_progress | 01/21/2030 00:01:00 | 02/01/2030 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
2039517 | YUCCA GT2 | PO | in_progress | 01/20/2031 00:01:00 | 01/31/2031 23:59:00 |  |  |  | Approved | MW | 19 | 19 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7728586 | YUCCA GT3 | PO | in_progress | 02/08/2027 00:01:00 | 03/08/2027 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Hot section overhaul / Reliability outage | Z13288 | 04/29/2026 06:49:11 MST
3535833 | YUCCA GT3 | PO | pending | 10/01/2027 00:01:00 | 11/15/2027 23:59:00 |  |  |  |  | MW | 52 | 52 | 0 | Generator protective relay and multipin connector replacement / Torque converter replacement | Z04648 | 04/27/2026 12:52:28 MST
11429683 | YUCCA GT3 | PO | in_progress | 02/14/2028 00:01:00 | 02/28/2028 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | integ-mig | 12/31/2023 22:00:00 MST
16285451 | YUCCA GT3 | PO | in_progress | 02/12/2029 00:01:00 | 02/26/2029 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | integ-mig | 12/31/2023 22:00:00 MST
16205953 | YUCCA GT3 | PO | in_progress | 02/11/2030 00:01:00 | 02/25/2030 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | integ-mig | 12/31/2023 22:00:00 MST
9222279 | YUCCA GT3 | PO | in_progress | 02/10/2031 00:01:00 | 02/25/2031 23:59:00 |  |  |  | Approved | MW | 55 | 55 | 0 | Reliability Outage | integ-mig | 12/31/2023 22:00:00 MST
3886428 | YUCCA GT4 | PO | in_progress | 11/02/2026 00:01:00 | 11/13/2026 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1298308 | YUCCA GT4 | PO | in_progress | 11/01/2027 00:01:00 | 11/12/2027 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
9076137 | YUCCA GT4 | PO | in_progress | 11/06/2028 00:01:00 | 11/17/2028 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
11701798 | YUCCA GT4 | PO | in_progress | 11/05/2029 00:01:00 | 11/19/2029 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
4668147 | YUCCA GT4 | PO | in_progress | 11/04/2030 00:01:00 | 11/18/2030 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
1559654 | YUCCA GT4 | PO | in_progress | 11/03/2031 00:01:00 | 11/17/2031 23:59:00 |  |  |  | Approved | MW | 54 | 54 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
15249250 | YUCCA GT5 | PO | in_progress | 03/08/2027 00:01:00 | 03/22/2027 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
15979288 | YUCCA GT5 | PO | in_progress | 03/06/2028 00:01:00 | 03/20/2028 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
7008399 | YUCCA GT5 | PO | in_progress | 03/12/2029 00:01:00 | 03/26/2029 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
11108718 | YUCCA GT5 | PO | in_progress | 03/11/2030 00:01:00 | 03/25/2030 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
12648423 | YUCCA GT5 | PO | in_progress | 03/10/2031 00:01:00 | 03/24/2031 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
4825111 | YUCCA GT6 | PO | in_progress | 03/08/2027 00:01:00 | 03/22/2027 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
16015022 | YUCCA GT6 | PO | in_progress | 03/06/2028 00:01:00 | 03/20/2028 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
11754556 | YUCCA GT6 | PO | in_progress | 03/12/2029 00:01:00 | 03/26/2029 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
14296719 | YUCCA GT6 | PO | in_progress | 03/11/2030 00:01:00 | 03/25/2030 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
8168090 | YUCCA GT6 | PO | in_progress | 03/10/2031 00:01:00 | 03/24/2031 23:59:00 |  |  |  | Approved | MW | 45 | 45 | 0 | Reliability outage | integ-mig | 12/31/2023 22:00:00 MST
8850223 | YUCCA TEMPORARY GENERATION | PO | in_progress | 10/01/2024 00:01:00 | 05/31/2026 23:59:00 | 10/01/2024 00:01:00 |  |  |  | MW | 50 | 50 | 0 | Out of season | Z17963 | 05/22/2025 07:55:16 MST